## Brief
AI Help List — Chad's Brief
Things Chad wants the AI to help with. Source-of-truth for the parser.
1. Construction Schedule — Phase Durations
Phase | Default Duration | Notes
Land Clearing | 2–5 days
Foundation (footing → slab pour) | 10 days
Framing | 20 days | Order cabinets when framing complete
Roofing | 3 days
Rough-In (Plumbing, HVAC, Electrical) | 15 days
Siding | 7 days
Insulation | 3 days
Drywall (hang, sand, finish) | 6 days
Flooring (Tile + Hardwood) | 15 days
Trim | 5 days
Painting (interior + exterior) | 15 days
Final Grade | 1 day
Landscaping & Irrigation prep | 7 days
2. Material Lead Times
Material | Lead Time | When to Order
Windows & Exterior Doors | 10–12 weeks | Order when contract signed
Plumbing Fixtures | Varies | Before framing starts (need in-wall valves at rough-in)
Electrical | Varies | Before framing
Cabinets | Measure-driven | Measure and order when framing complete
Flooring | 3–4 weeks | Order before drywall
Interior Doors | 2 weeks
3. Phase Checklists (24 lists, end-to-end)
# | Phase Checklist | Notes
1 | Precon Check List (model template — 44 items / 10 categories) | See Precon tab
2 | Sitework Check List
3 | Foundation Check List
4 | Pre-framing Check List
5 | Framing Check List
6 | Post-framing Check List
7 | Plumbing Rough Check List
8 | HVAC Rough Check List
9 | Electrical Rough Check List
10 | Siding & Porch Check List
11 | Insulation Rough Check List
12 | Drywall Rough Check List
13 | Cabinet Check List
14 | Countertop Check List
15 | Trim & Stairs Check List
16 | Paint Check List
17 | Tile Check List
18 | Wood Flooring Check List
19 | Plumbing Set Out Check List
20 | Electrical Set Out Check List
21 | HVAC Trim Out Check List
22 | Landscape & Irrigation Check List
23 | Final Paint Check List
24 | Final Punch Out Check List
4. Task Organization — Views
View | Frequency | Contents
Daily — Chad's Morning View | Every day | What's happening today across all jobs (tasks, deliveries, inspections, drop-dead dates)
Weekly Outlook | Mondays | What's scheduled this week per job, drop-dead dates this week, milestone meetings
Monthly Outlook | 1st of month | Scheduled deliveries / installs / inspections / drop-dead dates per job, % completion vs plan
Master Build-Out Schedule | Per project | Complete schedule with milestones, drop-dead order dates, estimated completion date
5. Auto-Notify Chad — Triggers
Trigger | Severity | Description
Selection Deadline Approaching | Warning | Approaching drop-dead order date for a selection still open (default 14 days out)
Weather Delay | Warning | Forecast precipitation or wind exceeds phase tolerance (concrete pour, framing, roofing, exterior paint)
Sub No-Show | Critical | Subcontractor not on site by 9am on a scheduled day
Material No-Show | Critical | Past scheduled delivery date with no confirmation
Inspection Failure / Reinspect | Critical | Inspection result = Fail or Reinspect required — phase reopens, schedule recomputes

## Precon Check List
Precon Check List
44 items across 10 categories — the model template for all phase checklists
Category | Checklist Item | Status | Notes
Client & Contract | Signed construction contract
Finalized scope of work defined
Allowances defined
Change order process defined
Payment schedule approved
Financing confirmed
Plans & Engineering | Final construction drawings complete
Structural engineering complete
Truss drawings ordered
Window & door schedule finalized & ordered
Electrical plan finalized
Selections | Exterior selections finalized
Windows & doors selected & ordered
Cabinets selected & ordered
Flooring selected
Tile selections finalized
Plumbing fixtures selected
Lighting fixtures selected
Appliances selected
Permitting | Building permit approved
Septic permit approved
HOA approval
Site Prep | Survey completed
Property corners marked
Utilities located (811)
Drainage plan confirmed
Subcontractors | Sitework contractor scheduled
Concrete contractor scheduled
Framer scheduled
MEP contractors scheduled
Materials | Windows ordered
Cabinets ordered
Trusses ordered
Lumber package ready
Budget | Final job budget completed
Sub bids locked
Contingency included
Schedule | Master schedule created
Long lead items aligned
Weekly lookahead ready
Meetings | Internal precon meeting completed
Client precon meeting completed